| Cross Town Projects |
| --- |
| Project |  | Timescales | Cost | Budget Line | Lead Officers Team | Councillor/ Council Involvement | Actual Cost | Delivery |
| BMX | Review siting, usage & condition of all BMX locations across the town, including: Harlescott Meole Springfield Greenfield Shorncliffe Upton Lane Moston Road (re-introduction) Sports Village (SC facility) |  | £40,000 | £18,000 Revenue £22,000 BMX Reserves £7122 LJC/Other | Gary Farmer (Committee) Adam Purnell (Community) Ian Thorpe (Grounds) | R&L – 03.04.19 F&GP – 08.04.19 |  | Late Summer after School Holidays |
| 01.02.19 – All site inspected and report being prepared for R&L Committee 03.04.19 03.04.19 – Report to R&L seeking prioritisation then tendering for surfacing works thereafter 03.04.19 – Committee Agreed Tendering for Surfacing & working on specification with staff measuring tracks 01.07.19 – Tender out – Closing date 30.08.19 30.09.19 – Tenders to be approved at F&GP 02.10.19 – Detail to be ratified by R&L |
| Street Lights | Conversion of SOXE Light heads to LED. Currently an audit is being carried out to determine column quality | To meet EU 2020 Deadline |  | £95,000 Street Lighting Reserves | Stuart Farmer (Committee) | R&L – 03.04.19 F&GP – 08.04.19 | £114,640 | 16 weeks from award of contract (31.07.19) |
| 01.02.19 – All tender documents prepared and uploaded onto STC Website and Contract Finder. Deadline for submission of Tenders 1.3.19 11.02.19 – 15 Companies have expressed interest in tendering 01.03.19 – 5 Tenders received – due diligence work undertaken 01.04.19 – Sample lighting in Quarry installed 03.04.19 – Report to Committee 03.04.19 – Budget Approved & Contractor appointed 24.04.19 – Mobilisation meeting with Contractor to discuss schedule of works, ordering of fitments and plans for stress testing columns 29.05.19 – Column stress testing received & Committee to consider options. Lanterns due for delivery w/c 3 June 2019 29.05.19 – R&L Committee REC Replacement of 12no Columns from 2018/19 allocated Capital Replacement Budget 01.07.19 – Replacement Columns & Heads arrived; PO for Western Power initiated; Potters/Allmarks discussing new column locations with Highways (Highways Portfolio Holder waived fees) 01.07.19 – LED Replacement well underway; retrofit of Quarry lanterns underway; Wall mounted lantern design agreed 01.09.19 – Wall mounted lamps arrived. Well over half way (200+). GIS updated with replacement lanterns. On track for completion by the time the clocks go back. TOTAL COMPLAINTS – 4 – all due to brightness and need for shields to counter light nuisance into properties |
| Toilets | Develop a programme of improvement of public conveniences (Decorations, Fittings, Deep Cleansing, including: Quarry Upper – Part of Quarry Vision Hills Lane Abbey Foregate Butcher Row Quarry Lower – Part of Quarry Vision – Wholescale Redesign |  | £20,000 £250,000 | £20,000 Revenue £250,000 N/Fund | Gary Farmer (Committee) Mark Harris (Buildings) Rob Plimmer (Cleansing) Helen Ball (Project Mgt) Andy Watkin (Project Mgt) Stuart Farmer (Project Mgt) |  |  |  |
| 04.07.19 – Invitation to join the Quarry Development Officers Group 15.07.19 – Town Clerk met with Team Leisure (commissioned to write the Quarry Pool Feasibility Report). Potential for incorporating external using toilets was discussed as an option) |
| Footpaths/Cycleways | Review the location of footpaths within individual wards – both on STC land and as part of the wide PROW network Distribute Ward Maps showing PROW Develop proposals for improvements to the network |  | £100,000 | £100,000 Town Projects Reserve | Matt Wilcoxon (Grounds) Jim Goldsmith (Grounds) | R&L – 29.05.19 F&GP – 03.06.19 |  | Autumn/Winter 2019 |
| 11.02.19 – Countryside Team reviewing footpath provision on STC land. 08.04.19 – Contact Councillors re paths in their wards 29.05.19 – Report to Committee 29.05.19 – R&L Committee REC Note the report & instruct Officers to send details to all members for their consideration of footpath areas in their wards 30.09.19 – Report to F&GP with recommendation 02.10.19 – Report to R&L |
| Defibrillators | Identify areas of need for defibrillators – Potentially through Cllr Grant |  | No Budget Allocation |  |  |  |  |  |
| 29.05.19 – Consideration purchase of Defibrillator for Weeping Cross 29.05.19 – R&L REC Purchase of Defibrillator for Weeping Cross Depot 17.09.19 – Defibrillator ordered |
| Community Centres | Review the Town Council involvement in Community Centres including: Ditherington Castlefields Grange Youth Centre Springfield Kynaston Shrewsbury South Urban Extension Meet Place, Meole |  |  | £20,000 Revenue £20,000 Youth Facilities Reserves £20,000 N/Fund | Gary Farmer (Committee) Mark Harris (Building) Adam Purnell (Community) | R&L – 03.04.19 F&GP – 08.04.19 |  |  |
| Meet Place (£20,000) 28.01.19 – Meeting with Meole Estate Community Association to discuss the extension to Meet Place 12.02.19 – Helen Ball & Cllr Laurens to attend MECA AGM 01.04.19 – Awaiting funding decisions form Housing Plus 13.05.19 – Still awaiting funding decisions from Housing Plus – chasing email sent 15.05.19 – Youth Committee suggested Portacabin on Mary Webb Road as an Option B 19.05.19 – R&L Committee REC Contact Severnside CEO for update and explore option for Portacabin on Mary Webb Road 06.06.19 – Town Clerk met with Assistant Director Development at Housing Plus to progress project 01.09.19 – Town Clerk awaiting catch-up with Housing Plus regarding revised quotes 12.09.19 – Update from Housing Plus – willingness to work with MECA & contribute £20k subject to ratification of tenant benefit. Association currently seeking formalisation of status. Grange Youth Centre 18.02.19 – Kitchen to be installed in Grange Youth Centre 14.04.19 – Facility launched as a Community Centre 29.05.19 – Quotes for decoration at the Grange Youth - £900 for Toilets and High Roof – Recommend David Wood Painter & Decorator 29.05.19 – R&L Committee REC Proceed with appointment of Decorator – works order initiated WORKS COMPLETE Castlefields Community Centre 01.04.19 – Quotes for Soffits, Roofing & Wooden Doors being revisited 08.04.19 – Castlefields Community Centre Committee to be given contact details of designer of Grange Kitchen to design works 29.04.19 - Soffits, Roofing & Doors contract awarded – work to be done in Summer Holidays on the instruction of the Community Association 23.08.19 – Works to Soffits, Roofing & Doors commenced 30.09.19 – Kitchen quotes to be approved by F&GP |
| Countyside Sites | Interpretation boards – Pilot in Reabrook |  | £10,000 | £10,000 Solar | Gary Farmer (Committee) Matt Wilcoxon (Grounds) | R&L – 29.05.19 F&GP – 03.06.19 |  | Autumn 2019 |
| 11.02.19 – Locations being investigated 01.04.19 – Reviewing potential content 29.05.19 – Detail of content to Committee |
| Key Ward Projects |
| Project |  | Timescales | Cost | Budget Line | Lead Officers Team | Councillor Involvement | Actual Cost | Delivery |
| Abbey Gardens ABBEY WARD | Develop a Vision for Improvement to area to mirror quality of the Quarry (improved planting of shrub beds, interpretation boards and cutting regimes) – would require additional staff resources | Member to meet officers on-site to determine Vision | No Budget Allocation £10,000 | £10,000 Revenue | Gary Farmer (Committee) Debbie Entwistle (Planting) | Hannah Fraser F&GP –15.07.19 R&L – 17.07.19 |  |  |
| 01.04.19 – Member of staff re-located to cover Abbey Gardens/Castlewalk/Abbey/Town Centre. GF met with Team Leader to discuss initial tidy up to determine level of works needed 01.07.19 – Supplementary planting planned for Autumn, following meet up with ward member 17.09.19 – Dates sought from ward members regarding improvement options |
| Castlefields Community Centre CASTLEFIELDS WARD | Improvements to Kitchen, Soffits, Roofing & landscaping of beds outside | 2019/20 | £20,000 | £20,000 Revenue | Gary Farmer (Committee) Mark Harris (Building) | Alan Mosley R&L – 03.04.19 F&GP – 08.04.19 |  | Summer 2019 |
| 01.02.19 – Previous quotations for external works including replacement soffits, replacement doors and external decoration being revisited 01.04.19 – Quotes for Soffits, Roofing & Wooden Doors being revisited 08.04.19 – Castlefields Community Centre Committee to be given contact details of designer of Grange Kitchen to design works 29.04.19 - Soffits, Roofing & Doors contract awarded – work to be done in Summer Holidays on the instruction of the Community Association 23.08.19 – Works to Soffits, Roofing & Doors commenced 30.09.19 – Kitchen quotes to be approved by F&GP |
| Springfield Recreation Ground COLUMN WARD | Improvements to walkways around the Mere – part of Countryside | 2019/20 | £10,000 | £10,000 Solar | Gary Farmer (Committee) Matt Wilcoxon (Grounds) Jim Goldsmith (Grounds) | Jane Mackenzie R&L – 29.05.19 F&GP – 03.06.19 |  |  |
| 11.02.19 – Countryside Team reviewing footpath provision on STC land. 29.05.19 – Report to Committee 30.09.19 – Report to F&GP with recommendation 02.10.19 – Report to R&L |
| Little Harlescott Lane BMX HARLESCOTT WARD | Enhancements to BMX | 2019/20 | £7,000 estimated | £7122 LJC/Other | Gary Farmer (Committee) Adam Purnell (Community) Ian Thorpe (Grounds) | Ioan Jones R&L – 03.04.19 F&GP – 08.04.19 |  |  |
| 01.02.19 – All site inspected and report being prepared for R&L Committee 03.04.19 03.04.19 – Report to R&L seeking prioritisation then tendering for surfacing works thereafter. Working on specification 01.07.19 – Tender out – Closing date 30.08.19 30.09.19 – Works to be approved at F&GP 02.10.19 – Report to R&L |
| Meet Place MEOLE WARD | Support for an Extension to improve community use on site – Likely cost of project £60k (£20k from Trinity Church; £20k from Severnside Housing) | 2019/20 | £20,000 | £20,000 N/Fund | Helen Ball (Committee) | Nic Laurens |  |  |
| 04.02.19 – Meeting with MECA to discuss plans. 11.02.19 - Enquiries to be made with Trinity Church and Severnside Housing to confirm funding commitment (By end of Feb). It was ascertained that Severnside needed to be the lead organisation given their ownership.(HB) 12.02.19 – Helen Ball & Cllr Laurens to attend MECA AGM 02.04.19 – Severnside Housing chased on funding commitment 13.05.19 – Still awaiting funding decisions from Housing Plus – chasing email sent 06.06.19 – Town Clerk met with Assistant Director Development at Housing Plus to progress project 01.09.19 – Town Clerk awaiting catch-up with Housing Plus regarding revised quotes 12.09.19 – Update from Housing Plus – willingness to work with MECA & contribute £20k subject to ratification of tenant benefit. Association currently seeking formalisation of status. |
| Monkmoor River Banks MONKMOOR WARD | Improved accessibility – potential ERDF funding – need match funding – project linked to Monkmoor Community Woodland | 2019/20 | £40k | £40,000 N/Fund | Gary Farmer (Committee) Matt Wilcoxon (Grounds) Jim Goldsmith (Grounds) | Pam Moseley |  | October 2019 (awaiting outcome of ESIF Bid) |
| 01.02.19 – Monkmoor Community Woodland to be submitted as part of the Shropshire Wildlife Trust 2019 submissions to ERDF 17.05.19 – Part of SWT “Fresh Water First Extension” bid to the European Structural Investment Fund - Application submitted. Decision due late Summer. 17.09.19 – Update sought |
| Monkmoor Community woods MONKMOOR WARD | Enhancement to Countryside land footpaths & cycleways – project linked to Monkmoor River Banks | 2019/20 | £8,000 estimated | £8,000 Solar | Matt Wilcoxon (Grounds) Jim Goldsmith (Grounds) | Pam Moseley |  | October 2019 (awaiting outcome of ESIF Bid) |
| 11.02.19 – Countryside Team reviewing footpath provision on STC land. Report to R&L Committee 03.14.19 – likely to be tied in with the construction of the Monkmoor Community Woodland project which is awaiting outcome of ESIF bid 30.09.19 – Report to F&GP with recommendation 02.10.19 – Report to R&L |  |  |  |  |  |  |  |  |
| County Ground PORTHILL WARD | Extension to the Sports Pavilion to enhance usage (currently facility used 7 days a week for cricket, football, canoeing, shufflers, rounders) Improvement to Grounds (s106 money from Copthorne Barracks) | 2019/21 | £400k | £115,000 S106 £400,000 N/Fund | Helen Ball (Committee) Mark Harris (Building) Stuart Farmer (Tendering) Mike Cox (Bookings) Danny Powell (Grounds) | R&L – 29.05.19 F&GP – 03.06.19 |  | Summer 2020 |
| 22.01.19 – Discussions with Beacon Cricket Club to detail both current and potential usage of an extended Pavilion 06.02.19 – Ring-fenced funding pot discussed with Architect with a view to amending the design to fit the budget 24.08.19 – Discussions with ECB regarding funding opportunities and potential for lease arrangements 30.09.19 – F&GP to consider appetite for any long-term lease to run the facility, which in turn could open up options for external funding |
| Roundhill Green Play Area QUARRY & COTON HILL WARD | Improvements to Play facilities & wetpour | 2019/20 | £30,000 | £30,000 Play Area Reserves | Gary Farmer (Committee) Debbie Entwistle (Play) | R&L – 29.05.19 F&GP – 03.06.19 |  | Summer 2019 |
| 01.03.19 – Preparation for tender specification in readiness for April tender invitation 01.04.19 – Still investigating solutions to subsidence/surfacing problem 01.07.19 – Tender prepared – Contract value increased to £35k to accommodate additional surfacing needs (addition to be taken out of Play Area Maintenance budget) 27.08.19 – Tender Awarded 01.11.19 – Start Date |
| Dana Footpath QUARRY & COTON HILL WARD | Enhancements to path to achieve disabled friendly access to the town | 2019/20 | £50,000 | £50,000 Dana Footpath Reserves | Gary Farmer (Committee) Helen Ball (Committee) |  |  | Summer 2019 |
| 06.02.19 – SC still working on the final discharge of the planning conditions and the scheduled monument consent. Conversations taking place between WSP and Shropshire Council to ensure that is dealt with a quickly as possible. A Meeting is being scheduled w/c 11.02.19 to conclude this (Update from Andy Wilde – SC) 25.03.19 – Update from Andy Wilde – Discharge of planning conditions & meeting with SHS April, Legals & mobilisation of contract May/June, Work on site June/July 24.05.19 – Contact made with Andy Wilde. Awaiting the outcome of a meeting with the SHS 30.05.19 to agree a meeting with stakeholders. Requested a discussion with Kier as a matter of urgency ahead of summer bedding out to determine any disruption works to the Raised Bed & Long Border. 01.07.19 – Project Start Meeting being convened |
| Castlewalk Recreation Ground UNDERDALE WARD | Levelling of the surface to protect the tip cap – discussions have taken place with EA & SC Public Protection – Contaminated Land Section Development of the Recreation Ground as a Countryside Site - Improvement of vistas along the riverbank |  | £30,000 | £30,000 Revenue | Mike Cox (Committee) Mike Pugh (Levelling) Stuart Farmer (Tendering) Danny Powell (Grounds) | F&GP –15.07.19 R&L – 17.07.19 |  | Late Summer/Early Autumn depending on ground conditions |
| 01.02.19 – Initial discussion with Shropshire Council Public Protection & Environment Agency regarding licence to deposit soil |
| Monkmoor Recreation Ground UNDERDALE WARD | Improvements to the Pavilion – Security Fencing Replacement All Weather Surface, Floodlights & Fencing Tennis facility enhancement – Old courts into use/possible cover for recently refurbished courts Enhancements to existing CCTV / replace cameras (£25k of Solar Funding ringfenced for Quarry & Monkmoor Cameras) |  | Estimate £250,000 | £140,000 N/Fund £110,000 Pitch Reserve £10,000 Solar | Gary Farmer (Committee) Stuart Farmer (Tendering) | R&L – 03.04.19 F&GP – 08.04.19 | £186,000 or £199,000 depending on netting/fencing option | Summer 2019 11 weeks from award of contract |
| 05.12.18 – Order raised for fencing to Pavilion & fitted (funded through Revenue Budget) 01.02.19 – Old Courts cleaned and available for use 11.02.19 – Specification for tender being finalised in readiness for upload onto STC Website & Contract Finder 15.02.19 – Tender Advert – closing date 15.03.19 15.03.19 – 2 Tenders – Due diligence 03.04.19 – Committee 03.04.19 – Tender awarded. Contractor working on plans for submission to the Planning Authority 10.05.19 – Users consulted regarding preference for fixed or curtain – fencing. Majority in favour of fixed fencing. Contractor notified. 29.05.19 – Planning application submitted – determination dated 04.07.19 29.05.19 – External decorations of Pavilion & Bungalow – 3 quotes (£5010; £5971; £4565) – Recommend David Wood Painter & Decorator 09.08.19 - Decoration complete 20.07.19 – Planning Permission Granted 13.09.19 – Meeting with Durasport to discuss start date (provisional start date – Mid-October but subject to climatic conditions and heavy football fixtures due to SAHA clubs being displaced from Radbrook Rec) |

| Projects Completed |
| --- |
| Project |  | Timescales | Cost | Budget Line | Lead Officers Team | Cllr/ Council Involvement | Actual Cost | Delivery |
| Grange Youth Centre HARLESCOTT WARD | Enhancements to convert to a Community Centre | 2018/19 School Term | £10,000 | £20,000 Youth Facilities Reserve | Helen Ball (Committee) Adam Purnell (Community) Mark Harris (Building) | Youth Services Committee | £6500 (Kitchen) £15000 (Fittings) | April 2019 |
| 18.02.19 – Kitchen to be installed in Grange Youth Centre 14.04.19 – Planned Launch as a Community Centre pending agreement on branding COMPLETE |
| Grangefields Play Area MEOLE WARD | Improvements To Play Area | 2019/20 | £30,000 | £30,000 S106 | Gary Farmer (Committee) Debbie Entwistle (Play) | Nic Laurens | £30,000 | April 2019 |
| 13.11.18 – Invitation to Tender – Closing Date 14.01.19 14.01.19 – Tenders Received 29.01.19 – Award of Contract to Ray Parry for possible installation (pending weather conditions) by 11.04.19 (in time for Easter Holidays) 01.04.19 – Started on site COMPLETE |
| Bank Farm Road Play Area RADBROOK WARD | Improvements To Play Area | 2019/20 | £30,000 | £30,000 S106 | Gary Farmer (Committee) Debbie Entwistle (Play) | Keith Roberts |  | April 2019 |
| 13.11.18 – Invitation to Tender – Closing Date 14.01.19 14.01.19 – Tenders Received 29.01.19 – Award of Contract to Ray Parry for possible installation (pending weather conditions) by 11.04.19 (in time for Easter Holidays) 01.04.19 – Awaiting improvement of ground conditions COMPLETE |
| Big Town Plan | Continue involvement in the BTP Board Allocate £50k a year for the next 3 years to part develop the plan alongside SC & BID |  | £150,000 | £50,000 for next 3 years Revenue | Helen Ball (Committee) | Alan Mosley |  |  |
| 24.01.19 – BTP Meeting to discuss Project Board, Co-ordinator post and Independent Chair 21.03.19 – BTP Board agreed JD for co-ordinator 10.05.19 – Co-ordinator & Independent Chair Job Adverts went live 28.05.19 – Co-ordinator Post 7 applicants – shortlisted to 3. Independent Chair Post 2 applicants – both to be interviewed 17.06.19 – Interview date for Co-ordinator Post. Both Independent Chair applicants to meet the BTP Board COMPLETE |
| Shrewsbury in Bloom | Expansions of Bloom activity to facilitate other community groups – Use Bloom Sponsorship |  |  |  | Gary Farmer (Committee) | Keith Roberts R&L - 03.04.19 |  |  |
| 30.01.19 – Shrewsbury in Bloom Met to discuss 2019 Campaign. Bloom Chairman to write to all Councillors regarding any communities locally that could be supported by Bloom 28.03.19 – Discussions on route taking into account new areas COMPLETE |
| Mousecroft Pool RADBROOK WARD | Installation of a borehole to maintain water levels |  | £10,000 (Fishing Revenue) | £10,000 Fishing Reserves | Mike Cox (Committee) Matt Wilcoxon (Grounds) |  |  |  |
| 14.01.19 – Coppicing of trees around Mousecroft Pool to open up the pool and reduce pull on water from treestock 01.04.19 – Pool dredges and banks reinforced and lined with clay layer – review water levels to determine need for borehole 30.04.19 – Fisheries monitoring levels COMPLETE |
| Church Road Recreation Ground MEOLE WARD | Improvements to Play Area Footpath between hardstanding Area and School to facilitate park & stride | 2019/20 | £17,000 Currently being costed | £17,000 Revenue | Gary Farmer (Committee) Debbie Entwistle (Play) Danny Powell (Grounds) Mark Preece (Grounds) | Nic Laurens R&L – 29.05.19 F&GP – 03.06.19 |  | July 2019 |
| 28.01.19 – Meeting with MVRA to discuss plans (HB) 04.02.19 – Grasscrete path installed from hard standing area to school path & existing concrete path edged 01.03.19 – Preparation for tender specification in readiness for April tender invitation 01.04.19 – Tender Advert – closing date 30.04.19 10.05.19 – Tender awarded – start date 08.07.19 COMPLETE |
| Heathgates Allotments CASTLEFIELDS WARD | Purchase & Installation of a pre-fabricated Community Shed on the Castlefields side of the Allotments | 2019/20 | £15,000 | £15,000 Allotment Reserves | Gary Farmer (Committee) Mark Harris (Building) | R&L – 29.05.19 F&GP – 03.06.19 |  | Summer 2019 |
| 14.02.19 – Heathgates Allotments Association to meet to determine preferences for Community Shed 01.04.19 – Heathgates Allotments seeking quotes. STC to commission ground works & Utilities 29.05.19 – Report on Community Shed to Committee 29.05.19 – R&L Committee REC Agree choice of Community Shed and specification for Groundworks 01.07.19 – Groundworks contract awarded to Rob Allmark; shed ordered 02.09.19 – Ground Works commenced 09.09.19 – Shed installed WORKS COMPLETE |
| Radbrook Recreation Ground COPTHORNE WARD | Pitch Levelling Parking Changing facilities |  | £150,000 estimated | £60,000 S106 £90,000 N/Fund | Stuart Farmer (Committee) Danny Powell (Grounds) Mark Preece (Grounds) | R&L – 03.04.19 F&GP – 08.04.19 | £150,000 | June 2019 |
| 11.02.19 – Specification for tender being finalised in readiness for upload onto STC Website & Contract Finder 01.03.19 – Tender Advertised 01.04.19 – 5 Tenders received – due diligence 03.04.19 – Meet preferred tenderer 03.04.19 - Contractor awarded – planned start June 2019 13.05.19 – Letter drop to 100 residents 29.05.19 – Start date w/c 10 June 2019 01.07.19 – Started on site; Archery club located to Monkmoor Rec; SAHA relocated to various pitches 03.09.19 - Drainage, levelling & seeding complete 06.09.19 – Installation of Pedestrian Gate 30.09.19 – Scheduled first Cut 01.11.19 – Scheduled removal of fencing 01.09.20 – Scheduled use for football WORKS COMPLETE |