## Action Plan
Climate Change Action Plan
No. | Category | Action | Reduction in Carbon | Deadline | Total cost | Allocation from CE budget | Co-partner/Co-benefit action | Specific Actions and Progress | Lead Officer
1 | Mobilisation and Leadership | Organisational Review of Policies to align with Climate Emergency Commitment | Medium | 2022-07-01 | Negligible | 0 |  | COMPLETE Climate Change policy agreed. All other STC policies reviwed. | Amanda Spencer
2 | Mobilisation and Leadership | Climate Emergency Page on Website | Low | 2022-03-01 | 10000 | 0 |  | COMPLETE | Amanda Spencer
3 | Mobilisation and Leadership | Make reference to Climate Emergency and need for renewable energy measures when commenting on planning applications | Low | 2022-07-01 | Negligible | 0 |  | COMPLETE - Reference made Climate Change & Renewable Energy in both Local Plan Consultation and Planning White Paper consultation | Amanda Spencer
4 | Mobilisation and Leadership | Add Climate Emergency References in all Invitations for Tender and add to the evaluation process. Wherever possible carry out whole life carbon assessment in procurement process | Low | 2020-07-01 | Negligible | 0 |  | COMPLETE - New section added in all Invitations to Tender | Stu Farmer
5 | Mobilisation and Leadership | Publicise key elimination commitment | Low | 2021-04-01 | Negligible | 0 |  | COMPLETE | Helen Ball
6 | Mobilisation and Leadership | Join Global Covenant of Mayors | Low | 2020-07-01 | Negligible | 0 |  | COMPLETE | Helen Ball
7 | Mobilisation and Leadership | Write to Sec State DEFRA | Low | 2020-07-01 | Negligible | 0 |  | COMPLETE | Helen Ball
8 | Energy Efficiency | Undertake Carbon Footprint Audit | Medium | 2022-09-01 | Negligible | 0 |  | COMPLETE | Amanda Spencer/Andy Watkin
9 | Energy Efficiency | Review Investment Schedule for replacement vehicles, plant & machinery and purchase appliances with high energy efficiency rating - Write this into procedures and policies | Medium | 2022-12-01 | TBC | Specific allocation to be decided on a case by case basis |  | COMPLETE Reduce, Remove and Recycle will become a basic premise of the Climate Change policy (under action 1.). Policy will be based upon end of life replacement. Examples of appliances purchased: New energy efficient boiler installed at the Grange Youth Centre (Cost: £4370), Blower in Greenhouse. | Stu Farmer/Kevin Price
10 | Energy Efficiency | Undertake a Buildings Audit to ascertain any efficiency measures | Medium | 2024-04-01 | TBC | TBC |  | COMPLETE | Amanda Spencer
11 | Energy Efficiency | Replace and install LED/solar lights across the town including the Quarry | Medium | 2022-01-01 | 138671 | 43671 |  | COMPLETE | Stu Farmer
12 | Energy Efficiency | Investigate potential to be involved in Weir Hydro Scheme | High | 2023-12-01 |  |  |  | Under discussion | Helen Ball
13 | Energy Efficiency | Review energy provider renewable energy commissioning | High | 2020-07-01 | Negligible | 0 |  | COMPLETE Switched to 100% Green Energy | Andy Watkin
14 | Energy Efficiency | Explore potential for installing Solar/Wind mitigating measures on Council Land/Buildings | High | 2024-04-01 | TBC | TBC |  | LEP discussion. Need expertise on buildings audit. | Andy Watkin/Stu Farmer
15 | Active Travel | Development of local cycling and walking infrastructure plans and map | Medium | 2021-04-01 | £26,581 plus £48,269 | Phase 1 £2,658 (10%) Phase 2 10% of final spend |  | COMPLETE Footpath Improvements | Matt Wilcoxon
[8 empty] | Mini Holland Bid (link to Movement Strategy) | Helen Ball
16 | Zero Emissions Transport | Source local materials rather than from a distance | Medium | 2020-12-01 | Negligible | 0 |  | COMPLETE Tendering process has been aligned to this objective | Stu Farmer
17 | Zero Emissions Transport | Investigate more remote working and flexible working patterns of staff | Low | 2021-04-01 | Negligible | 0 |  | COMPLETE | Amanda Spencer
18 | Zero Emissions Transport | Review how staff travel to and within work and the the Council’s Mileage Policy to determine most efficient mechanism for staff to travel around. Explore the need and level of bicycle storage in town council premises. Instigate a Cycle Purchase Scheme. | Medium | 2021-11-01 | Negligible |  |  | COMPLETE EVP at Weeping Cross installed | Stu Farmer
|  |  |  | 2022-07-01 |  |  |  | COMPLETE | Amanda Spencer/Andy Watkin
19 | Zero Emissions Transport | Explore electric Vehicle options for fleet and Explore infrastructure requirements and power capacity for electric vehicles | Medium | 2022-07-01 | 50000 | 4704 |  | COMPLETE Vehicles purchased: Electric Mule (£16,704). Van on order. Electric tools purchased for Castle. | Stu Farmer
20 | Reduced Consumption and Waste | Ensure all Contractors have a “Zero to Landfill” policy | Medium | 2020-12-01 | Negligible | 0 |  | COMPLETE Now included in the Tender Proposals. Publicised process to the public | Stu Farmer
21 | Reduced Consumption and Waste | Continue replacement of planting vessels with built-in water reservoirs to reduce the need for watering | Low | 2024-04-01 | Negligible |  |  | COMPLETE | Gary Farmer
22 | Reduced Consumption and Waste | Ensure all waste is recycled and reused wherever possible | Medium | 2021-07-01 | Negligible | 0 |  | COMPLETE Bulit into contract | Gary Farmer
23 | Reduced Consumption and Waste | Investigate the use of pyrolysis for all waste - This will be done in conjunction with a partner such as Shropshire Council | Medium | 2022-12-01 |  |  |  |  | Jim Goldsmith
24 | Adaption and Resilience | Purchase and use only Peat-Free Compost | Medium | 2020-12-01 | Negligible | 0 |  | COMPLETE | Gary Farmer
25 | Adaption and Resilience | Explore drought resilient planting options | Medium | 2022-07-01 | Negligible | 0 |  | COMPLETE | Gary Farmer
26 | Adaption and Resilience | Reduce irrigation needs | Medium |  | Negligible | 0 |  | COMPLETE | Gary Farmer
27 | Adaption and Resilience | Review Tree Policy | Medium | 2022-12-01 | 500 | 500 |  | COMPLETE | Gary Farmer
28 | Engaging the Community | Utilise the Admag Wrap around to promote climate efficiency | Low | 2021-12-01 | Negligible |  |  | COMPLETE Moved to web based newsletter with effect from 2021 | Hils Humphreys
29 | Engaging the Community | Develop information about STC's approach to Climate Change in key areas such as Castle Walk | Low | 2023-07-01 |  |  |  | COMPLETE | Jim Goldsmith
30 | Engaging the Community | Develop comms plan and public communications event on all of the work STC do in this area | Low |  | Negligible |  |  | COMPLETE | Amanda Spencer
31 | Engaging the Community | Develop Volunteering Opportunities | Low |  | Negligible |  |  | Develop a programme for volunteering | Matt Wilcoxon
32 | Engaging the Community | Initiate a Climate Emergency Grant Fund to support community initiatives | Low |  |  |  |  | Under discussion | Helen Ball/Andy Watkin
33 | Engaging the Community | Include Climate Emergency Category in Mayor’s Awards | Low | 2020-12-01 | Negligible | 0 |  | COMPLETE | Helen Ball
34 | Engaging the Community | Develop a Youth Forum | Low |  | Negligible | 0 |  | COMPLETE | Andy Hall
35 | Engaging the Community | Develop Climate Emergency as a Shrewsbury in Bloom Theme | Low | 2021-12-01 | Negligible | 0 |  | COMPLETE | Hils Humphreys
36 | Engaging STC Staff and Members | Use Shrewsbury Cups at Council Events and Meetings | Low | 2020-12-01 | Negligible | 0 |  | COMPLETE | Helen Ball